## Ark1
Website for Lofthus frukt & saft
Start date: Monday 27.04.2020 |  |  |  |  | Week | 1 |  |  |  |  | 2 |  |  |  |  | 3 |  |  |  |  | 4 |  |  |  |  | 5 |  |  |  |  | 6 |  |  |  |  | 7 |  |  |  |  | 8 |  |  |  |  | 9
Expected end date: Thursday 25.06.2020 |  |  |  |  | Days | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
Activity | People assigned | Role | Duration (week) | Duration (days)
Planning the process | All | All |  | 2 | bar: 1 M to 1 T
Layout/Page structure
Plan layout for website | Carina | Visual designer | 1 | bar: 1 W to 2 F
Plan structure of pages | Carina | Visual designer | 1 | bar: 2 W to 3 F
Photo shoot | Johnny | Photographer |  | 3 | bar: 2 F to 3 T
Edit photos | Johnny | Photographer | 1 | bar: 3 F to 4 Th
Code and link all pages | Yvonne | front-dev | 2 |  | 3 Th: Debug/test while working
Payment/delivery
Find payment options | Kim | Project manager | 1 | bar: 1 W to 2 T
Find delivery companies | Kim | Project manager | 1 | bar: 2 M to 2 F
Add payment options | Yvonne | front-dev |  | 4 | bar: 3 W to 4 M
Add delivery options | Yvonne | front-dev |  | 4 | bar: 4 T to 4 F
Company & production
Write company info | Phil | Copywriter | 2 | bar: 1 W to 3 T
Write production process | Phil | Copywriter | 1 | bar: 3 W to 4 W
Write newsletters | Phil | Copywriter | 1 | bar: 4 W to 5 T
Write campaigns | Phil | Copywriter | 1 | bar: 5 T to 6 M
Style and code pages | Yvonne | front-dev | 1 |  | 6 M: Company info/production
Remaining coding
Add only available products | Yvonne | front-dev |  | 4 | bar: 6 M to 6 Th
Add shopping cart | Yvonne | front-dev |  | 3 | bar: 6 Th to 7 M
Add order confirmation | Yvonne | front-dev |  | 3 | bar: 7 T to 7 Th
Add sales and campaign | Yvonne | front-dev |  | 3 | bar: 7 F to 8 T
Final implementation/testrun | All | All |  | 8 | bar: 8 W to 9 F
[26 empty] | Specification | [6 empty] | Finished website | [7 empty] | Key meetings